# Velaris Launch Content Strategy

January 5-15, 2025 | 10-Day Sprint

# Core Strategy: LinkedIn-First + Product Hunt

With no existing audience, your highest-ROI path is founder-led LinkedIn content (company pages get 2% reach vs personal profiles at 20-30%) combined with a well-executed Product Hunt launch. This combination can generate 25-150 signups in 10 days.

# 10-Day Content Calendar

| Day | Theme | Content & Actions |
| --- | --- | --- |
| 1-2 | Origin Story | "Why we built this" — focus on problem, not product yet. Set up Product Hunt teaser page. |
| 3-4 | Pain + Value | Carousel: "5 signs your brand is invisible to AI." Free framework post (no pitch). |
| 5-6 | Social Proof | Beta feedback screenshots. Feature teaser (30s video/GIF). LinkedIn poll on pain points. |
| 7-8 | Countdown | "3 days until launch" with countdown graphic. Introduce scarcity: founding member pricing. |
| 9-10 | Launch! | Product Hunt launch (12:01 AM PT). Multi-post LinkedIn blitz. Reply to every comment personally. |

# Two Commitment Scenarios

| Full (2-3 hrs/day) | Middle (30-60 min/day) |
| --- | --- |
| - Daily LinkedIn post + Stories - 50+ strategic comments/day - Product Hunt + Hacker News launch - $300-500 paid (Reddit + LinkedIn) - Personalized outreach/DMs Expected: 50-150 signups | - Daily LinkedIn post only - 15-20 strategic comments/day - Product Hunt launch only - $100 paid (Reddit OR LinkedIn) - Skip: HN, press, podcast outreach Expected: 20-50 signups |

# LinkedIn Algorithm Quick Wins

- Post Tue-Thu, 8-11 AM (Wed 10 AM = peak). Never post twice within 12 hours.

- Polls get 1.64x reach, carousels 1.45x. Text-only = 0.88x (avoid).

- First hour is critical — have colleagues engage immediately.

- Saves > Comments > Likes. Ask questions that prompt saves ("bookmark this").

- Comment on influencer posts within 15 min of posting for maximum visibility.

# Low-Budget Paid Allocation

| Budget | Reddit Ads | LinkedIn | Expected Leads |
| --- | --- | --- | --- |
| $100 | $60 | $40 boost | 1-5 |
| $300 | $150 | $150 Lead Gen | 5-15 |
| $500 | $200 | $250 Lead Gen + $50 retarget | 10-25 |

Reddit CPC: $0.50-2 vs LinkedIn: $5-10. Target r/SaaS, r/marketing, r/Entrepreneur for best ROI.

# Product Hunt Launch Checklist

- Launch Tuesday-Thursday at 12:01 AM Pacific for full 24-hour window

- Set up "Coming Soon" teaser page NOW to collect supporters

- Prepare assets: 1270×760px images, demo video, one-sentence tagline

- Have supporters search for you (don't send direct links — PH detects this)

- Reply to EVERY comment personally — this signals quality to the algorithm

# Behavioral Science Principles to Apply

- Loss aversion: "Founding pricing ends Jan 20" beats "Get early access" by 50%

- Social proof: "Join 247 marketers on the waitlist" — even small numbers work

- Curiosity gap: Each post answers one question while raising another

- Countdown timers: Add 30-50% to conversion — start Day 7, not earlier (avoid fatigue)

Start Day 1 content today. The clock is running.